Safe Takoma

Report, June 2007

July 2, 2007

Prepared by Safe Takoma, Incorporated on behalf of the

Takoma DC Neighborhood Association

7106 Piney Branch Road

Washington, DC 20012

Contact: Sara Green, Secretary, Safe Takoma Incorporated, 202-829-8802

Reference

Grant Agreement between the District of Columbia, Metropolitan Police Department, and the Takoma DC Neighborhood Association acting “as the fiduciary agent for the Subgrantee” on the project, the cross-jurisdictional, collaborative, crime prevention program operated by Safe Takoma, Incorporated (the “Subgrantee”).

2.5	Progress Reports. The grantee shall submit monthly progress reports to the Grant Monitor by the 10th day of each month of service, regarding status of the funds expended and reports on progress made toward each project objective.

Funds expended

Funds expended in June 2007: $0

Prior District funds expended: $0

Prior funds expended, Takoma Park MD reimbursement: $380

Status

The Safe Takoma program continued in its planning phase in June 2007.  As described in the Program Budget and Narrative, Budget Amendment 1 dated June 1, 2007, steps in that first phase are:

PHASE I – Planning & Mobilization

- Creation of organizational structures by Safe Takoma Incorporated in consultation with funders.

- Inception of a Program Steering Committee with community and government stakeholder participation.

- Program planning; development of a detailed work plan and schedule; development of metrics and mechanism for program evaluation.

Safe Takoma has no equipment, leases, employees or financial obligations.

Progress made toward project objectives

Because the program is still in the Planning & Mobilization phases, we do not yet have measures of progress to report toward “overall goals” as described in Section 5.8 of the Safe Takoma Grant Agreement.  Organizationally, in June 2007 Safe Takoma –

- Submitted an amended budget on June 1 and received grant-monitor approval for limited organizational expenditures.

- Discussed the Safe Takoma-Takoma DC Neighborhood Association relationship with TDCNA officers by phone and e-mail and at the June 12 TDCNA board meeting.

- Submitted a May 2007 status and budget report as required by the grant agreement Section 4.3 Sources and Uses of Funds to the MPD on June 15.

- Held Board of Directors meetings on June 15.

- Worked with grant monitor Cmdr. Hilton Burton to clarify TDCNA-STI handling of District funds.

- Took steps to satisfy administrative requirements per the grant agreement.

Regarding accomplishment of General Requirements listed in Section 5.8:

Coordinating meetings among diverse groups including Takoma-area businesses, school and recreation groups, neighborhood and tenant associations, churches, Advisory Neighborhood Commission 4B, the City Council of Takoma Park, Maryland, and other affected stakeholders.

  - Safe Takoma held a community stakeholders meeting at Victory Tower on June 7 toward this end.

  - Met with Ms. Monica Megyes, Mediation Program Manager of the Conflict Resolution Center of Montgomery County, Inc. (CRCMC).

  - Responded to e-mail contact from Ashley Johnson, Peer Mediation Coordinator for Coolidge Sr. HS, wanting to meet & work with Safe Takoma Inc.